## Introduction
Project Name |  |  | Electric Blender
Ref Document |  | HSI
Ref Version |  | V1.2
Auther |  | Abdelrahman Ali
Last update |  | 2020-02-07
History
Version | Auther |  | Date | Change
0.1 | A.Ali |  | 31/01/2020 | Initial creation
0.2 | A.Ali |  | 2020-07-02 | Update the review & close old points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V1.0 | HSI | Page 1 | Status of document must be changed from Draft to Proposed and then Released after accomplishing cross review on it. I expect if cross review was done by another team member , the status of document should be Released. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | HSI | Last page | There is no Reference table for the reference document , even HSI should have one and the reference is the customer Requirement for the product | Accepted | Resolved |  | Accepted
29/01/2020 | A.Ali | V1.0 | HSI | List of Contents | Update the number of Document History section and update the page numbering in List of Contents because can’t navigate to any of the sections mentioned in this list of contents. | Accepted | Resolved |  | Refused
29/01/2020 | A.Ali | V1.0 | HSI | Page 6 | You could add a requirement ID to Pins Connection section above the table. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | HSI | Page 6 & 7 | Instead of use TAG-ID you could replace it with Req_ID and put requirement IDs above the description of requirements not below. | Accepted | Resolved |  | Open
29/01/2020 | A.Ali | V1.0 | HSI | Page 7 | In section 3.3.5 ATMEGA32 : There is no need to add this kind of information as it is outside the scope of HSI document. | Accepted | Open | AAL 07/02/2020 : You need to add the microcontroller specifications (AVR ATMEGA 32) Internal peripherals have and could add an image for uc layout if you would. | Resolved
2020-07-02 | A.Ali | V1.2 | HSI | Page 2 | Document Status should include one row and should be updated with the final status of document from the document history. | Accepted | Open
2020-07-02 | A.Ali | V1.2 | HSI | Page 3 | There is a subtitle below the table of contents , it should be removed if you don’t need it. Also, in pages you mentioned that you’ve 10 pages and that isn’t correct because you just have 7 pages. | Accepted | Open
2020-07-02 | A.Ali | V1.2 | HSI | Page 6 & 7 | You need to add the requirement IDs above the requirement description and should write the implementation type (SW or HW) like that #Imp: HW beside the requirement ID. | Accepted | Open |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open