## Introduction
Project Name |  |  | Electric Blender
Ref Document |  | CYRS
Ref Version |  | V1.1
Auther |  | Abdelrahman Ali
Last update |  | 2020-07-02
History
Version | Auther |  | Date | Change
0.1 | A.Ali |  | 31/01/2020 | Initial creation
0.2 | A.Ali |  | 2020-07-02 | Close old points from week 1 & Add new points

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V1.0 | CYRS | Page 1 | Neither the Status nor the version and the project ID has been written in the first page of CYRS document , you could add a header table appears in each page of the document. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Page 3 | Document history has to be at the start before Table of Contents. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Table of Contents | Update Table of Content page numbering for all sections. | Accepted | Resolved |  | Accepted
29/01/2020 | A.Ali | V1.0 | CYRS | Last page | There is no Reference table for the reference document , even CYRS should have one and the reference is the customer Requirement for the product | Accepted | Resolved |  | Refused
29/01/2020 | A.Ali | V1.0 | CYRS | Features | The CYRS describe the overall system and shall be more abstracted from the level of SW. You need to make your requirement more clarified from the system level prospective. Req_ PO2_EBL_Electric_Blender_CYRS_001-1.0: - There’s no need to mention the first speed with duty cycle and instead of that you could say for example : the blender shall operate between 3 different speeds (Speed1 → Speed 2 → Speed 3) triggered by a button. - Also, there isn’t a customer specification states that the first speed with duty cycle of 50%. You shouldn’t take a step forward and guess something not mentioned by the customer in CRS until taking customer approval. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Features | All Req need to be updated with system level prospective not SW prospective. (Req_ PO2_EBL_Electric_Blender_CYRS_002-1.0) | Accepted | Resolved
2020-07-02 | A.Ali | V1.1 | CYRS | Reference Table | Reference table title should be before the table not after it. | Refused | Open | AALI 9/2/2020 : No , it’s after the table not before it. Please, refer to the title of Reference Table. Reference table title is already before the table not after it | Open
2020-07-02 | A.Ali | V1.1 | CYRS | Table of Contents | Can’t navigate to table of figures page numbering from Table of Contents. | Refused | Open | AALI 9/2/2020 : Can’t navigate to the correct page of Figure 1 when press on it from the table of Figures. the table of figures is in the same page of table of content, could you clarify your point more ? | Resolved
2020-07-02 | A.Ali | V1.1 | CYRS | Document History | Add separate date for rework & review in Document History table even if the work is done in the same day. According to the plan, CYRS review planned to start on 5/2/2020. | Accepted | Resolved
2020-07-02 | A.Ali | V1.1 | CYRS | System Requirements | As we discussed all HW requirements shall be added to HSI document, so in this requirement : Req_ PO2_EBL_Electric_Blender_CYRS_002-1.0 , you could add a HW requirement illustrate more what is the required implementation need to be considered from HW prospective. Also, the same in requirement Req_ PO2_EBL_Electric_Blender_CYRS_003-1.0 | Accepted | Open | AALI 9/2/2020: This point is still not solved yet.
2020-07-02 | A.Ali | V1.1 | CYRS | System Requirements | Missing update the requirements version after modifying them. | Accepted | Resolved |  | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
2020-07-02 | A.Ali | V1.1 | CYRS | System Requirements | You need to add more requirements in CYRS. Ex: you can add requirements which describe how to handle the communication between the inputs devices & o/p devices (Motor driver & Motor). | Accepted | Resolved |  | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open