## Project Plan
PROJECT PLAN
| PROJECT TITLE |  | START DATE
| Electric Blender - PO2_EBL |  | 2020-01-18 |  |  | PROJECT DURATION
| PROJECT TEAM LEADER |  | END DATE |  |  | in days
| Mostafa Ramadan |  | 2020-02-22 |  |  | 36
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | Estimated START DATE | Estimated END DATE | Actual START DATE | Actual END DATE | DURATION in days | Descriptions | STATUS
1 | PROJECT INITIATION | In Progress |  | 2020-01-21 | 2020-01-24 | 2020-01-21 | 2020-01-24 | 4 |  | Not Started
1.1 | – Project Plan | Complete | Mostafa Ramadan | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-22 | 2 |  | In Progress
1.1.1 | – SIQ Document | Complete | Fatima Gomaa | 2020-01-21 | 2020-01-22 | 2020-01-21 | 2020-01-22 | 2 |  | Complete
1.2 | – CYRS Document | Complete | Mohamed Anis | 2020-01-21 | 2020-01-22 | 2020-01-21 | 2020-01-22 | 2 |  | On Hold
1.3 | – SRS Document | Complete | Ahmed Genedi | 2020-01-22 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 1
1.4 | – HSI Document | Complete | Mohamed Anwar - Esraa Mansour | 2020-01-22 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 1
1.5 | – RTM Document | Complete | Mostafa Ramadan | 2020-01-22 | 2020-01-23 | 2020-01-22 | 2020-01-24 | 3
1.6 | – Edit RTM Document | Complete | Mostafa Ramadan | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-02-05 | 2 | Adding the Requirment IDs from the CRYS to the RTM Document so the requirments can be traced and which component in the downstream is covering them
1.7 | – Edit CYRS Document | Complete | Mohamed Anis - Fatima Gomaa | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-02-04 | 1 | Accepting and Adding the Review Points to the CYRS document to change it from draft status to proposed status
1.8 | – Review CYRS Document | Complete | Ahmed Genedi | 2020-02-05 | 2020-02-05 | 2020-02-06 | 2020-02-06 | 1 | Review on the CYRS document and check if there are no missing requirements to change its status from proposed status to released status
1.9 | – Edit HSI Document | Complete | Mohamed Anwar - Esraa Mansour | 2020-02-04 | 2020-02-05 | 2020-02-04 | 2020-02-05 | 2 | Accepting and Adding the Review Points to the HSI document to change it from draft status to proposed status
1.(10) | – Review HSI Document | Complete | Fatima Gomaa | 2020-02-05 | 2020-02-05 | 2020-02-08 | 2020-02-08 | 1 | Review on the HSI document and check if there are no missing requirements to change its status from proposed to released
1.11 | – Edit SRS Document | Complete | Ahmed Genedi | 2020-02-06 | 2020-02-06 | 2020-02-07 | 2020-02-07 | 1 | Editting and Adding the Requirments coming from upstream document (CYRS document) to change it from deaft status to proposed
1.12 | – Review SRS Document | Complete | Mostafa Ramadan | 2020-02-06 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 1 | Review on the SRS document and check if there are no missing requirements to change it from proposed to released
1.13 | – Edit CYRS Document | Complete | Mohamed Anis | 2020-02-09 | 2020-02-09 | 2020-02-09 | 2020-02-09 | 1 | Edit the CYRS document based on the points in the CYRS review sheet
1.14 | – Review CYRS Document | Complete | Esraa Mansour | 2020-02-09 | 2020-02-10 | 2020-02-09 | 2020-02-09 | 1 | Review on the CYRS document to check if it match the review points in the CYRS review document
1.15 | – Edit HSI Document | Complete | Mohamed Anwar | 2020-02-09 | 2020-02-10 | 2020-02-09 | 2020-02-09 | 1 | Edit the HSI document based on the review points in the HSI review sheet
1.16 | – Review HSI Document | Complete | Mostafa Ramadan | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 1 | Review the HSI document to check if it meets the review points in the HSI review document
1.17 | – Edit SRS Document | Complete | Ahmed Genedi | 2020-02-09 | 2020-02-09 | 2020-02-09 | 2020-02-09 | 1 | Edit the SRS document based on the review points in the SRS review document
1.18 | – Review SRS Document | Complete | Fatima Gomaa | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 1 | Review on the SRS document to check if it meets the review points in the SRS review document
1.19 | – Edit SRS Document | Not Started | Ahmed Genedi | 2020-02-21 | 2020-02-22 |  |  | 1 | Edit the SRS document based on the new added requirements in the CYRS document.
1.(20) | Review SRS Document | Not Started | Mostafa Ramadan | 2020-02-22 | 2020-02-22 |  |  | 1 | Review on the SRS document to check if all the requirements in it are covering all the requirements in the CYRS.
1.18 |  | Not Started | [5 empty] | 1
1.18 |  | Not Started | [5 empty] | 1
2 | PROJECT DEFINITION AND PLANNING | Not Started | [5 empty] | 1
2.1 | – Scope & Goal Setting | Not Started |  |  |  | 1
2.2 | – Budget | Not Started |  |  |  | 1
2.3 | – Communication Plan | Not Started |  |  |  | 1
2.4 | – Risk Management | Not Started |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION | Not Started |  |  |  | 1
3.1 | – Status & Tracking | Not Started |  |  |  | 1
3.2 | – KPIs | Not Started |  |  |  | 1
3.2.1 | –– Monitoring | Not Started |  |  |  | 1
3.2.2 | –– Forecasts | Not Started |  |  |  | 1
3.3 | – Project Updates | Not Started |  |  |  | 1
3.3.1 | –– Chart Updates | Not Started |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING | Not Started |  |  |  | 1
4.1 | – Project Objectives | Not Started |  |  |  | 1
4.2 | – Quality Deliverables | Not Started |  |  |  | 1
4.3 | – Effort & Cost Tracking | Not Started |  |  |  | 1
4.4 | – Project Performance | Not Started |  |  |  | 1