## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | V1.2
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V1.0 | CYRS | Page 1 | Neither the Status nor the version and the project ID has been written in the first page of CYRS document , you could add a header table appears in each page of the document. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Page 3 | - Document history has to be at the start before Table of Contents. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Table of Contents | Update Table of Content page numbering for all sections. | Accepted | Resolved |  | Accepted
29/01/2020 | A.Ali | V1.0 | CYRS | Last page | There is no Reference table for the reference document , even CYRS should have one and the reference is the customer Requirement for the product | Accepted | Resolved |  | Refused
29/01/2020 | A.Ali | V1.0 | CYRS | Features | The CYRS describe the overall system and shall be more abstracted from the level of SW. You need to make your requirement more clarified from the system level prospective. Req_ PO2_EBL_Electric_Blender_CYRS_001-1.0: - There’s no need to mention the first speed with duty cycle and instead of that you could say for example : the blender shall operate between 3 different speeds (Speed1 → Speed 2 → Speed 3) triggered by a button. - Also, there isn’t a customer specification states that the first speed with duty cycle of 50%. You shouldn’t take a step forward and guess something not mentioned by the customer in CRS until taking customer approval. | Accepted | Resolved
29/01/2020 | A.Ali | V1.0 | CYRS | Features | All Req need to be updated with system level prospective not SW prospective. (Req_ PO2_EBL_Electric_Blender_CYRS_002-1.0) | Accepted | Resolved
Open
Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open