## Introduction
Project Name |  |  | Digital Watch
Ref Document |  | CYRS
Ref Version |  | V1.2
Auther |  | Tarek Sharaby
Last update |  | 24/01/2020
History
Version | Auther |  | Date | Change
0.1 | T.Sharaby |  | 24/01/2020 | Initial creation

## Cross review points
Entry Date | Reviewer | Detection version | Name of file | Page/Line/Section/Entity | Open point : description of problem | Decision | Status | Comment
29/01/2020 | A.Ali | V1.0 | HSI | Page 1 | Status of document must be changed from Draft to Proposed and then Released after accomplishing cross review on it. I expect if cross review was done by another team member , the status of document should be Released. | Accepted | Open
29/01/2020 | A.Ali | V1.0 | HSI | Last page | There is no Reference table for the reference document , even HSI should have one and the reference is the customer Requirement for the product | Accepted | Open |  | Accepted
29/01/2020 | A.Ali | V1.0 | HSI | List of Contents | Update the number of Document History section and update the page numbering in List of Contents because can’t navigate to any of the sections mentioned in this list of contents. | Accepted | Open |  | Refused
29/01/2020 | A.Ali | V1.0 | HSI | Page 6 | You could add a requirement ID to Pins Connection section above the table. | Accepted | Open
29/01/2020 | A.Ali | V1.0 | HSI | Page 6 & 7 | Instead of use TAG-ID you could replace it with Req_ID and put requirement IDs above the description of requirements not below. | Accepted | Open |  | Open
29/01/2020 | A.Ali | V1.0 | HSI | Page 7 | In section 3.3.5 ATMEGA32 : There is no need to add this kind of information as it is outside the scope of HSI document. | Accepted | Open |  | Resolved
[9 empty] | Decision | whether to accept the open point if you see applicable and valid or to refuse it and give a justification in the comment field whether you accept , then update with the action you did , or refuse with justification
[9 empty] | Status | Is for the reviewer he check the fix of the open point and check if the fix is ok or still open