## Project Plan
PROJECT PLAN
| PROJECT TITLE |  | START DATE
| Electric Blender - PO2_EBL |  | 2020-01-18 |  |  | PROJECT DURATION
| PROJECT TEAM LEADER |  | END DATE |  |  | in days
| Mostafa Ramadan |  | 2020-02-22 |  |  | 36
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT INITIATION | In Progress |  | 2020-01-21 | 2020-01-24 | 4 |  | Not Started
1.1 | – Project Plan | In Progress | Mostafa Ramadan | 2020-01-21 | 2020-01-21 | 1 |  | In Progress
1.1.1 | – SIQ Document | In Progress | Fatima Gomaa | 2020-01-21 | 2020-01-22 | 2 |  | Complete
1.2 | – CYRS Document | In Progress | Mohamed Anis | 2020-01-21 | 2020-01-22 | 2 |  | On Hold
1.3 | – SRS Document | Not Started | Ahmed Genedi | 2020-01-22 | 2020-01-23 | 2
1.4 | – HSI Document | Not Started | Mohamed Anwar - Esraa Mansour | 2020-01-22 | 2020-01-23 | 2
1.5 | – RTM Document | In Progress | Mostafa Ramadan | 2020-01-22 | 2020-01-23 | 2
2 | PROJECT DEFINITION AND PLANNING | Not Started |  |  |  | 1
2.1 | – Scope & Goal Setting | Not Started |  |  |  | 1
2.2 | – Budget | Not Started |  |  |  | 1
2.3 | – Communication Plan | Not Started |  |  |  | 1
2.4 | – Risk Management | Not Started |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION | Not Started |  |  |  | 1
3.1 | – Status & Tracking | Not Started |  |  |  | 1
3.2 | – KPIs | Not Started |  |  |  | 1
3.2.1 | –– Monitoring | Not Started |  |  |  | 1
3.2.2 | –– Forecasts | Not Started |  |  |  | 1
3.3 | – Project Updates | Not Started |  |  |  | 1
3.3.1 | –– Chart Updates | Not Started |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING | Not Started |  |  |  | 1
4.1 | – Project Objectives | Not Started |  |  |  | 1
4.2 | – Quality Deliverables | Not Started |  |  |  | 1
4.3 | – Effort & Cost Tracking | Not Started |  |  |  | 1
4.4 | – Project Performance | Not Started |  |  |  | 1